## Sheet1
Project | Scheduling system project
last updated
|  |  | Rank from 1 lowest to 5 highest | Rank from 1 lowest to 5 highest
Risk ID | Description | Trigger | Probability | Impact | Score | Schedule Impact | Financial Impact | Owner | Response | Response Strategy | Expected Results | Status | Notes
1 | None of the vendor systems can provide the functionality required in the timeframe and budget required |  |  |  | 0
2 | Systems aren’t compatible with hospital equipment |  |  |  | 0
3 | Scheduling delays push expenditures past the grant expiration date |  |  |  | 0
4 | Key resource is pulled onto a different project |  |  |  | 0
5 | Stakeholders disagree on required functionality |  |  |  | 0
6 | Scheduling staff aren’t made available for training sessions |  |  |  | 0
7 | Hospital emergency pulls resources away from project |  |  |  | 0
8 | Staff shortages alter the ability to schedule facilities to meet targets |  |  |  | 0
9 | Government grant managers change, altering requirements the hospital must accommodate |  |  |  | 0
10 | Health insurance policies change and alter the nature of the patients who expect care from the hospital |  |  |  | 0
11 | Facility design causes issues |  |  |  | 0
12 | Hospital diagnostic equipment electronically interfere with each other, compromising patient care |  |  |  | 0