## Sheet1
| Hospital Management | Finance | Project Management | IT | Facilities | Patient Services | Physician Services | Continuing Care and Resident Life | System Vendor
Project plan | A | I | R | C | C | C | C | I | C
Project budget | A | R,C | R | I | I | I | I | I | C
Process analysis | C |  | A,R |  | C | C | C | C | R
Process redesign | C |  | A,R |  | C | C | C | C | R
Scheduling system implementation | C |  | A,R |  | C | C | C | C | R
Cancer system implementation | C |  | A,R |  | C | C | C | C | R