## Sheet1
Audience | Information | Method | Schedule | Responsible Party
Customer/Sponsor | Forecast finish date and cost, any scope or objectives that are at risk | In-person | Friday at 11 am | Project manager
Management team | Summary of project status and performance, significant issues and successes | Bi-weekly email/Monthly in-person | Email every other Friday, management meeting Wednesdays at 10 am | Project manager
All team members | High-level status | Email | End of each week | Project manager
Finance | Cost performance, funding issues | Email | Ad-hoc | Project manager
Facilities | Scheduling information needed | Email | Ad-hoc | Project manager
Patient and Physician Services | Scheduling information needed | Email | Ad-hoc
Continuing Care and Resident Life | Scheduling information needed | Email | Ad-hoc
Project manager | Status updates | Email | Every Friday 4 P.M. | Team members
Change control board | Change requests | Updated shared documents | Every other Monday 2 P.M. | Change management lead
Project manager | Risk status | Updated shared documents | Every Monday 10 am | Risk management lead
Project manager | Development status, issues, successes | Telephone call | Every Monday 9 am | Vendor team lead